## Sprint Plan
| Prepare On | 2020-06-04
Double Rebate |  |  |  |  | Status | Comment
| Sprint 1 Hinge | 05 to 15 June | 1.1 | Profile Outline | ok
|  |  | 1.2 | Stline Slot | ok
|  |  | 1.3 | Hinge | ok
|  |  | 1.4 | Frame Fixing | ok
|  |  | 1.5 | Testing (Total Hinge)
| Sprint 2 Top View | 16 to 20 June | 2.1 | Top outline
|  |  | 2.2 | Slot
|  |  | 2.3 | Testing
| Sprint 3 Lock Side | 16 to 21 June | 3.1 | Lock profile outline & Internal
|  |  | 3.2 | Lock Feture | ok
|  |  | 3.3 | Testing
| Sprint 4 | 21 to 27 June | 4.1 | Overall Double Testing
|  |  | 4.2 | UI Win Form
Total
| Sprint 5 | 27 June to 2 July | 5.1 | Eyeshot Migration
Single Rebate |  |  |  | Single
| Sprint 6 Hinge | 01 to 12 July | 6 | Profile Outline
|  |  | 6.2 | Stline Slot
|  |  | 6.3 | Hinge
|  |  | 6.4 | Frame Fixing
|  |  | 6.5 | Testing (Total Hinge)
| Sprint 7 Top | 12 to 19 July | 7.1 | Top outline
|  |  | 7.2 | Slot
|  |  | 7.3 | Testing
| Sprint 8 Lock | 01 to 05 July | 8.1 | Lock profile outline & Internal
|  |  | 8.2 | Lock Feture
|  |  | 8.3 | Testing
| Sprint 9 | 19 to 25 July | 9.1 | Overall Double Testing
|  |  | 9.2 | UI Win Form
Total
| Sprint 10 | 25 to 30 July | 10.1 | Eyeshot Migration
| Sprint 11 | 25 to 30 July | 11.1 | Enhancement
| Sprint 12 | 2020-07-06 | Sprint 12 (MDF all option)
|  |  | 12.1 | DR Non Rated
|  |  | 12.2 | DR Fire Rated Min
|  |  | 12.3 | DR Fire Rated Max
|  |  | 12.4 | 38 mm Single
|  |  | 12.5 | Documentation
| Final Date | 2020-08-15 |  | Add some buffer time